## Product Backlog
Priority | Description | Estimate | Sprint | Total Story Points | 101
1 | We need to work out a script for the meetings with potential lenders | 0.5 | 1
2 | We need to contact the staff of the school of computing to make of list of equipment they are willing to lend out | 0.5 | 1
3 | For the database and website we need to meet client to work out what they want and what their main requirements are. | 2 | 1
4 | For each item we need to discuss with the item’s owner how long they want each item to be borrowed for. | 0.5 | 1
5 | Design database for the system | 13
6 | Build database from the specifications | 1
7 | Design the system with storyboards | 3 | 1
8 | I want the login system to use their Kent logins “dm458” so staff know who they are lending the equipment to | 2 | 1
9 | I want the website to match the University Of Kent's website’s layout and colour scheme so it gives off a professional feel | 2 | 1
10 | Create a website front end so people can access the booking system from a desktop | 8
11 | Specify different users permissions - Admin, Student,Faculty | 1
12 | I want to give staff the ability to add, remove and edit items | 2
13 | For the user i want them to be able to book items using the website /app | 3
14 | We need a basket/ checkout system so when the user makes a booking, there will be a list just before they check out -allow booking of multiple items | 3
15 | I want to have a system where the user can cancel and edit their bookings | 2
16 | With the editing and cancelling the bookings i want to have a function where they can repeat/ extend so they can keep using the equipment | ?
17 | I want to add a section of the site where it lists the main rules of using the system | 0.5
18 | For each item i want a more specific set of rules from each person lending the items | 1
19 | I want the staff to be able to set permissions on every single item that they are willing to lend out | 2
20 | Allow lender to view the current borrowing status of their items | 0.5
21 | System for borrower confirmation of returned item and condition | 1
22 | Damage and inventory facilities to record the condition and location of items in the catalogue | 3
23 | Restrictions on who can see equipment to be borrowed depending on their user status - do not show users things they cannot borrow | 0.5
24 | Allow staff to ban specific users from borrowing | 0.5
25 | Limit the amount a user can borrow at one time | 1
26 | I want to give the staff and the admin of the website and database to have the ability to recall an item if they need to | 2
27 | I want to add a staff override function so they can have the final say on who gets the equipment | ?
28 | Learn Android™ programming to assist in creating the app | 20
29 | Create Android™ front end to match style of website | 8
30 | I want the website to display correctly on all possible devices that can connect to the internet | 2
31 | For the system we need pictures of the equipment so the user knows what they are asking for | 3
32 | I want to have email sent out to the user to let them know what they have borrowed as well as the return date for each item | 0.5
33 | I want the website to have a search bar so they can find what they are looking for quickly as well as easy | 5
34 | I would like to have help prompts throughout the site to help people along the way | 3
35 | I would like to have a feedback section on the website so we can improve or remove functions that aren’t working | 3
36 | I want the website to have the different categories for the items to help people find what they are looking for | 1

## Sprint1 Backlog
Priority | Description | Estimate | Velocity | 10.5
1 | We need to work out a script for the meetings with potential lenders | 0.5
2 | We need to contact the staff of the school of computing to make of list of equipment they are willing to lend out | 0.5
3 | For the database and website we need to meet client to work out what they want and what their main requirements are. | 2
4 | For each item we need to discuss with the item’s owner how long they want each item to be borrowed for. | 0.5
7.1 | Design the website with storyboard | 1.5
7.2 | Design Android app with storyboard | 1.5
8.1 | Find out about using kent login system | 1
8.2 | Implement it into website | 1
9.1 | storyboard web pages to look like kent system | 1
9.2 | storyboard app to look like Kent system | 1