## Sheet1
Test Number | Test | Expected Result | Actual result | Error? | Fatal? | Changes? | Problem found?
1 | Does it look like part of the UoK system? | colour scheme = blue/white, UoK logo top left | colour scheme = blue/white, UoK logo top left | N | N | None | N/A
2 | Index page loads first? | Index.php is the first page to load | Index.php is the first page to load | N | N | None | N/A
3 | Bookings page for user to be available | My Bookings option in menu takes user to their personal booking page | My Bookings page is viewable | N | N | None | N/A
4 | Test Ajax loads the following pages: | [5 empty] | N/A
a | currentBookings.php | currentbookings page loads | currentbookings page loads | N | N | None | N/A
b | pastBookings.php | past bookings page loads | past bookings page loads | N | N | None | N/A
c | add_inventory.php | page to add an item loads | page to add an item loads | N | N | None | N/A
d | alltext.txt | loads text into drop down in add item page | loads text into drop down in add item page | N | N | None | N/A
e | tutorsonly.txt | loads text into drop down in add item page | loads text into drop down in add item page | N | N | None | N/A
f | withsupervision.txt | loads text into drop down in add item page | loads text into drop down in add item page | N | N | None | N/A
g | all_items.php | all items in catalogue page loads | all items in catalogue page loads | N | N | None | N/A
h | items_3.php | type 4 items page of catalogue loads | type 4 items page of catalogue loads | N | N | None | N/A
i | items_4.php | type 5 items page of catalogue loads | type 5 items page of catalogue loads | N | N | None | N/A
j | items_lego.php | lego items page of catalogue loads | lego items page of catalogue loads | N | N | None | N/A
k | items_pi.php | pi items page of catalogue loads | pi items page of catalogue loads | N | N | None | N/A
5 | Menu provides all options required for both users and admin | Menu has options to see current/past bookings, view catalogue, add items to inventory (admin) | Menu has options to see current/past bookings, view catalogue, add items to inventory (admin) | N | N | None | N/A
6 | Restrict options available in menu depending on status | Admin/staff should see more options than users | Admin/staff should see more options than users | N | N | None | N/A
7 | Test connection to Dragon database | Page tests connection to Dragon | Page displays "Connected successfully" | N | N | None | N/A
8 | Test the admin menu | Admin menu displays when Admin option is clicked | Admin menu loads and test content is displayed | N | N | None | N/A
9 | Different users should see different things within the navagation menu | when the use logs in they should see different things within the navagation menu, as a test only users "jd601" and "mh708" should see extra options | everyone was able to see all the options, which is not expected | Y | Y | Look at the if statement that runs this command | Y, the if statement was wrong, it was set to if($user =='jd601'¦¦'mh708') where it should have been if($user == 'jd601' ¦¦ $user == 'mh708')
10 | Different users should see different things within the navagation menu | when the use logs in they should see different things within the navagation menu, as a test only users "jd601" and "mh708" should see extra options | It now worked correctly and other users where not able to see the other options within the navagation menu | N | N | None | N/A
11 | have all the template pages been created? | clicking through the navagation, every link should have a template page created | not every page had a template page | Y | N | We will need to create the template pages. | Pages where not created yet
12 | have all the template pages been created? | clicking through the navagation, every link should have a template page created | All known pages(apart from one known and other yet to be decided) have template pages | N | N | None | N/A
13 | Testing the Agree Form | The agree form is just a test for now, but the user should not be able to click anything other than clicking within the form itself | The user was not able to click anying they where nto supposed to | N | N | None | N/A
14 | Testing the Agree Form | The user has to scroll down to the bottom of the agree form before they can agree | when the agree form has been scrolled to the bottom, then the options for agree appear | N | N | None | N/A
1.6.0
15 | Testing an ajax form to update the users name when they log in | When they fill out the form it should add their name to the database | it enterd a blank result | Y | Y | it will need to be editited to work | N/A
16 | Testing an ajax form to update the users name when they log in | When they fill out the form it should add their name to the database | it enterd a blank result | Y | Y | it will need to be editited to work | N/A
16 | Testing an ajax form to update the users name when they log in | When they fill out the form it should add their name to the database | it enterd a blank result | Y | Y | needs to be intergrated with the system | it now works and i dont know why
17 | User can enter full name | Users name appears in database | Name is in database | N | N | none | n/a
18 | User can enter campus | Users campus appears in database | Campus is in database | N | N | none | n/.a
19 | User can enter year group | Users year group is indatabase | Yeargroup is in databse | N | N | none | n/a
20 | purposly trying to break the code, this will be done by changing an element name within the brower and then inserting it into the database | Changing the value for an option within the option box should not effect the value thats inserted into the database | It added the modified value into the database | Y | Y | This can lead to a security risk, this will need to be changed, as users then would be able to enter anything into the database | we will need to check what the value is before adding it to the database
21 | purposly trying to break the code, this will be done by changing an element name within the brower and then inserting it into the database | Same as above but doing it with a different option box called year | It added a 0 value to the database because i typed a string instead of an int | Y | Y | Same as above | same as above
22 | purposly trying to break the code, this will be done by changing an element name within the brower and then inserting it into the database | Same as above but doing it with a different option box called year | It added the modified value into the database | Y | Y | same as above | same as above
23 | putting the agree form into the the php, this should show the agree form when it gets called rather than displayig it on a button click | The form should show if the user has not agreed to the form yet | The form did not show | y | y | Will need to find why the form did not show, will check the css | y
24 | putting the agree form into the the php, this should show the agree form when it gets called rather than displayig it on a button click | The form should show if the user has not agreed to the form yet | The form shown but without the correct css | y | n | need to make sure that all the css is set to display = true, this was beause with JS it was set to hidden | y, some of the divs where set to display= none, whch meant they where being loaded just not shown on the page
25 | putting the agree form into the the php, this should show the agree form when it gets called rather than displayig it on a button click | The form should show if the user has not agreed to the form yet | The form was shown | n | n | N/A | N/A
26 | does pressing agree add the agree value to the database | when pressing the agree button it should add the value 1 to the agreed sectio within the database, this making sure the user only needs to agree to the from once | The value was added to the datbase, although the value was added the first time, the from was shown twice and only disapeard on the second time of clicking | y | n | make sure the form only shows once | Still looking
27 | does the page dynamicly change based on the size of the screen on the home page? | when changing the size of the page the images and text should move into place accordingly | Yes it does | n | n | N\A | N\A | 2017-01-19
28 | does the page dynamicly change based on the size of the screen on the all catalog items page? | when changing the size of the page the images and text should move into place accordingly | Yes it does | n | n | N\A | N\A
29 | does the page dynamicly change based on the size of the screen on the Lego items page? | when changing the size of the page the images and text should move into place accordingly | Yes it does | n | n | N\A | N\A
30 | does the page dynamicly change based on the size of the screen on the Pi's items page? | when changing the size of the page the images and text should move into place accordingly | Yes it does | n | n | N\A | N\A
31 | does the page dynamicly change based on the size of the screen on the type 4 items page? | when changing the size of the page the images and text should move into place accordingly | Yes it does | n | n | N\A | N\A
32 | does the page dynamicly change based on the size of the screen on the all catalog items page? | when changing the size of the page the images and text should move into place accordingly | Yes it does | n | n | N\A | N\A
33 | Can you submit the new user from without filling in details (individually and together) | try each section of the form individually to see if it can be submitted | form only works properly if filled in fully and correctly on the first attempt | y | n | James is on it! trying to separate the functions on the page and create a run order | parts of the form do still allow you to leave them empty and still submit.....fixed, James spelled value wrong !!
34 | Can you submit the new user from without filling in details (individually and together) | try each section of the form individually to see if it can be submitted | It works now! | N | N | N\A | N\A
35 | Does pressing the catalog button now take you directly to the entire catalog? | when I press the catalog button it should take me to the page with all the items | to make navagation easier the navagation was changed so that there is only one catalogue link which the user can press, this page will display all of the items | n | n | N\A | N\A
36 | Does Clicking on an item take you directly to that items page? | I should be able to click on an item and it should load information about that item to me | it works correctly | n | n | N/A | N/A
37 | Does the item page show me the correct item information | when im on an items page it should show me the correct information about that item | it works correctly | n | n | N/A | N/A
38 | on an items page can you choose a date to book it | there should be a selection box with dates to book items | it works correctly
39 | when selecting a day to book the item you should not be able to select todays date | todays current date should not appear in the list of days | it works correctly
40 | does the second drop down menu allow you to choose how many days you would like to boook the item? | there should be another selection box on the page, this should allow me to select how many days I would like to book the item forq | it works correclty | n | n
41 | when pressing the book now button does it send you an email conforming that you have chosen to book this item | booking an item that im allowed to book, should send me an email saying which item I have booked, the person I have booked it from, they day I have choose to book it for and the day I should return the item | it works correctly
42 | does the email show you infromation about the item you choose to book | same as above | it works correctly
43 | does booking an item add one to your current bookings? | when I book an item it should tell me how many books I have | it works correcly, although I have to refresh the page to get it to update | y | n | find a way to update the variable on the page | The variable is not being updated
44 | does the booking go into the datebase? | when I book an item it should add it to the booking database | it works correclty | n | n
45 | does the correct booking date go into the database? | When selecting the day you would like to book the item it should put the correct date that you choose into the database | it put 00-00-0000 into the database which is wrong. it should have been the date chosen | y | y | change the value that gets put into the database | The problem was i was using the wrong varible when inserting it into the database
46 | does the correct booking date go into the database? | When selecting the day you would like to book the item it should put the correct date that you choose into the database | The correct date was put into the database | n | n | N/A | N/A
47 | does the return day show the correct day | it should show the day you book it, plus the days you have booked it for as the return day | this works correctly allough if you want to book it for one day it should allow me to do that | y | n | when adding the days together it should -1 to allow to count the day that its being booked for | the code does not count the day you pick it up as a day that it is being booked for
48 | does the booking then show up on the my bookings page | it should show the information about the booking you have made recently aswell as the other bookings you have made | this worked correctly | n | n | N/A | N/A
49 | is the search box working
50 | Does the search box prevent XSS attacks
51 | Does the search box prevent SQL injections?
52 | does the search box return the correct results | if I search for an item by name it should show me the items that have the same or simuilar name | it shows me the correct results, BUT it only checks against the first name of the item meaning that some items might not show | n | n | Look into a way where we check against the entire string of charactors within the items name | N/A
53 | does the search box work automatically | when typying it should automatically start searching the database for that item and displaying it | although it does work as intended, you can fine tune the results when you press return on the keyboard | n | n | look into a way where it can fine tune the results automatically without the use manually having to do it themseves | N/A
54 | Does Item Filtering work: | when selecting the item from the drop down box it should only show my items that have the same type as the ones choosen
55 | EEG Headset filtering | when I select EEG headset from the filter list it should only show me EEG headsets | this worked correctly | n | n | N/A | N/A
56 | Book Filtering | when selecting Books from the Filter list it should only show me books | this worked correctly | n | n | N/A | N/A
57 | Lego Filtering | When selecting Lego it should only show me lego on the page | this worked correctly | n | n | N/A | N/A
58 | Pi Filtering | when selecting PI it should only show me PI's | this worked correctly | n | n | N/A | N/A
59 | Filering an item and then searching | if I filter an item and then search for an item it should only only search for items with same type as the type selected | this did not work, this is because the search box returns new results that are not covered by the filtering meaning that it avoids the prevouis filter | y | n | This can be fixed with some PHP and SQL changes, the SQL Will need to be chnaged based on the filter selection meaning that we should also send the result of the filter to the PHP where it returns the result from the search, the PHP will also need an if statement, because if the filter is set to all items the SQL database does not have an item for all Items so, if filter is set to all items it shoulld run the the normal SQL selection but if the Filter has been set to books for example it should run an sql with a WHERE clause meaning that it would only run the search based on the type selected | yes
60 | does reszinig the my bookings page display the page in an easy to read format for phones | when I rezize the page it should fit for phone devices | it worked, although if you rezised the page back and then go to another page it goes back ot the bookings page which is bug | y | y | This could be fixed by removing the code that changes the page to fit on phones if the page is reloaded, or I could load both onto the page and then hide and display the other, this might be an easy fix | yes
61 | Can I Book an item that has already been booked on the days choosen
62 | can I book an item that has not been booked on the days chosen
63 | can I Edit the User inline without the box appearing on the page
64 | can I Edit the User inline without the box appearing on the page on Manage users page | when the admin wants to edit a users information they should be able to change one thing at a time if they should | this does not work, for example if the user wants to edit just a users name, then they would have to reset all of the other information to the same thing they already was | n | n | although it did not work as intended it still worked | yes
65 | can I Edit the User inline without the box appearing on the page on Manage users page | when the admin wants to edit a users information they should be able to change one thing at a time if they should | this now works, the user can edit one thing at a time withought having to refil the same information | n | n | N/A | N/A
66 | Can I edit the users UserType | I should be able to change the type of user the user is | this works as intended |  |  | N/A | N/A
67 | Can I Edit the users Year | I should be able to update the users year | this works as intended |  |  | N/A | N/A
68 | Can I edit the users Email | I should not be able to edit the users email | this works as intended |  |  | N/A | N/A
69 | Can I Edit the users campus | I should be able to edit the users campus | this did not work, this is because the value was gettting sent to the database, this was sending a string where it should be sending an int | y | y | change the value that gets put into the database | yes
70 | Can I Edit the users campus | I should be able to edit the users campus | This now works as intended | n | n | N/A | N/A
71 | Can I edit the users name | I should be able to edit the users name | this works as intended | n | n | N/A | N/A
72 | can I remove a user | pressing the remove user button should remove a user after a confimation box | this works as intended | n | n | N/A | N/A
73 | can I ban a user | pressing the ban user button should ban a user without removing them from the database | this works as intended | n | n | N/A | N/A
74 | can a user book an item if they have been banned | if the user has been banned they should not be able to book an item | this works as intended as the user cannot get to any page on the website | n | n | N/A | N/A
75 | when a user is banned can they accsess the website | they should not be able to accses any webpage on the site | this works as intended | n | n | N/A | N/A
76 | can I unban a banned user | if a user has been banned they should be able to be unbanned by an admin | this works as intended | n | n | N/A | N/A
77 | can a recently unbanned user accsess the website | if they have been unbanned they should be ablle to accsess the website as normal | this works as intended | n | n | N/A | N/A
78 | Can the admin make a new owner | on the make/remove owner page they should be able to make new owners | this works as intended once they have filled in the form | n | n | N/A | N/A
79 | can the admin remove someone as an owner | the admin should also be able to remove someone as an owner | this worked as intended | n | n | N/A | N/A
80 | can the admin edit an owners infromation | the user should also be able to edit an owners infromation | this works as intended | n | n | N/A | N/A
81 | Can an owner see all of their inventory | when navagating to the my inventory page the owner should be able to view all of their current inventory | this works as intended | n | n | N/A | N/A
82 | can a owner edit their inventory | The user should be able to edit the information about their item, such as name and condiiton | this works as intended | n | n | N/A | N/A
83 | can an owner remove their inventory | the user should be able to remove their own inventory | this works as intended | n | n | N/A | N/A
84 | can a user view the status of items that people want to book | the owner has to confirm a booking ,this allowing them to keep track of who is borrowing their items | this works as intended | n | n | N/A | N/A
85 | can an owner confirm a booking | if the owner accepts the booking condions they should be able to confirm the booking | this works as intended | n | n | N/A | N/A
86 | can an owner decline a bookin | if the owner does not accept the booking condions they should be able to deny the booking | this works as intended | n | n | N/A | N/A
87 | can a owner select that the item has been returned | if the item has been returned the owner should be able to say that they have recived the item back | this works as intended | n | n | N/A | N/A
88 | can an owner view the types of agreements | the owner should be able to see the agreements on the system, this allowing them to choose which one they might want to user | this works as intended | n | n | N/A | N/A
89 | can an owner view others agreements | the owner might want to view other peoples agreements that they might want to use themselves | this works as intended | n | n | N/A | N/A
90 | can an owner upload an agreement | on the page where they can upload an agreement they should be able to upload a txt file | this works as intended | n | n | N/A | N/A
91 | can an staff member add an item if they have not been set to an owner | if an staff member has not been set as an owner yet then they should not be able to upload an item | this works but not 100% the item does not get added but the image still uploads | y | y | if the staff has not been set as an owner yet then they shoould not have the navagation option, this can be fixed with an if statement on the php | yes
92 | can an owner add an item | if the staff has been set to an owner they should be able to upload a new item | this works as intended | n | n | N/A | N/A
93 | can an owner add a item name | the owner should be able to add an item name | this works as intended | n | n | N/A | N/A
94 | can an owner add an item type | the owner should be able to add an item type | this works as intended | n | n | N/A | N/A
95 | can an owner set an item agreement | the owner should be able to select an item agreement | this works as intended | n | n | N/A | N/A
96 | can an owner set an item restiction | the owner should be able to set an item restiction | this works as intended | n | n | N/A | N/A
97 | can an owner set if the item needs supervision | the owner should be able to set if they want the item to be supervised | this works as intended | n | n | N/A | N/A
98 | can an owner set the items condition | the owner hsould be able to set the items condition | this works as intended | n | n | N/A | N/A
99 | can an own upload an image | the owner should be able to add an item image | this works as intended | n | n | N/A | N/A
100 | can the owner view the agrement they have choosen on the same page when they're adding an item | if the owner has selected an agreement they should be able to view the current agreement just in case they want to check it | this works as intended | n | n | N/A | N/A
101 | does the new item show in the catalogue | the new item should appear in the catalogue | this works as intended | n | n | N/A | N/A
102 | does the new items information show correclty | the item should be uploaded with the correct infromation | this works as intended | n | n | N/A | N/A
103 | does the new item have the correct image | the image should be the one uploaded | this works as intended | n | n | N/A | N/A
104 | does the item show under the correct type | the item should have the type that the user has choosen | this works as intended | n | n | N/A | N/A
105 | can an owner change the type of their item | if the user has pressed the wrong type they should be able to change it | this works as intended | n | n | N/A | N/A
106
107
108
109
110
111
112
113
114
115